## Scheduler Zero
VOLECULE
We don't execute. We only verify.
PROJECT | V04F01 — Madhav Arambol Residence (S+4 + Terrace + Mumty), Arambol, Goa |  |  |  | FRAME FINISH
DOCUMENT | Scheduler Zero (Sch-0) — Baseline Structural Programme ¦ Progress overlay as of V04F01-06 · 18-Sep-2026 |  |  |  | 2027-04-28
BASIS | Contractor structural programme (footings → mumty). Frame only — excludes finishes, waterproofing, MEP fit-out & handover. |  |  |  | 366
BASELINE START | 2026-04-27 | [26 empty] | AS OF 18-SEP-2026
[8 empty] | APR 2026 | MAY 2026 |  |  |  | JUN 2026 |  |  |  |  | JUL 2026 |  |  |  | AUG 2026 |  |  |  |  | SEP 2026 |  |  |  | OCT 2026 |  |  |  | NOV 2026 |  |  |  |  | DEC 2026 |  |  |  | JAN 2027 |  |  |  | FEB 2027 |  |  |  | MAR 2027 |  |  |  |  | APR 2027
WORK | ACTIVITY | PRED. | DUR (d) | START | FINISH | STATUS @ ENTRY | DATE OF COMPLETION | time axis 2026-04-27 to 2027-04-26
FOUNDATION & SUBSTRUCTURE
W1 | Excavation in Hard Rock up to 1.5 m (Footings) | — | 7 | 2026-04-27 | 2026-05-04 | Completed | 2026-05-04 | bar: 2026-04-27 to 2026-05-04
W2 | Soiling | W1 | 4 | 2026-05-04 | 2026-05-08 | Completed | 2026-05-08 | bar: 2026-05-04
W3 | PCC for Footings | W2 | 4 | 2026-05-08 | 2026-05-12 | Completed | 2026-05-12 | bar: 2026-05-04 to 2026-05-11
W4 | Shuttering for Footing Boxes | W3 | 7 | 2026-05-12 | 2026-05-19 | Completed | 2026-05-19 | bar: 2026-05-11 to 2026-05-18
W5 | Tieing of Foundation Jaali & Column | W4 | 7 | 2026-05-19 | 2026-05-26 | Completed | 2026-05-26 | bar: 2026-05-18 to 2026-05-25
W6 | Checking of Steel | W5 | 1 | 2026-05-26 | 2026-05-27 | Completed | 2026-05-27 | bar: 2026-05-25
W7 | Casting of Footings | W6 | 1 | 2026-05-27 | 2026-05-28 | Completed | 2026-05-28 | bar: 2026-05-25
R.C.C. WORKS — STUB COLUMN & PLINTH
W8 | Line-out & Starter for Stub Column | W7 | 2 | 2026-05-28 | 2026-05-30 | Completed | 2026-05-30 | bar: 2026-05-25
W9 | Shuttering for Stub Column | W8 | 4 | 2026-05-30 | 2026-06-03 | Completed | 2026-06-03 | bar: 2026-05-25 to 2026-06-01
W10 | Casting of Stub Column | W9 | 2 | 2026-06-03 | 2026-06-05 | Completed | 2026-06-05 | bar: 2026-06-01
W11 | Excavation of Plinth Beams | W10 | 4 | 2026-06-05 | 2026-06-09 | Completed | 2026-06-09 | bar: 2026-06-01 to 2026-06-08
W12 | PCC Below | W11 | 4 | 2026-06-09 | 2026-06-13 | Completed | 2026-06-13 | bar: 2026-06-08
W13 | Masonry Below Plinth | W12 | 6 | 2026-06-13 | 2026-06-19 | Completed | 2026-06-19 | bar: 2026-06-08 to 2026-06-15
W14 | Shuttering for Plinth Beam | W13 | 7 | 2026-06-19 | 2026-06-26 | Completed | 2026-06-26 | bar: 2026-06-15 to 2026-06-22
W15 | Tieing of Reinforcement | W14 | 5 | 2026-06-26 | 2026-07-01 | Completed | 2026-07-01 | bar: 2026-06-22 to 2026-06-29
W16 | Checking of Steel | W15 | 1 | 2026-07-01 | 2026-07-02 | Completed | 2026-07-02 | bar: 2026-06-29
W17 | Concreting of Plinth Beam | W16 | 2 | 2026-07-02 | 2026-07-04 | Completed | 2026-07-04 | bar: 2026-06-29
W18 | De-shuttering of Plinth Beam | W17 | 1 | 2026-07-04 | 2026-07-05 | Completed | 2026-07-05 | bar: 2026-06-29
W19 | Backfilling in Plinth | W18 | 4 | 2026-07-05 | 2026-07-09 | Completed | 2026-07-09 | bar: 2026-06-29 to 2026-07-06
W20 | Rubble Soling in Plinth | W19 | 6 | 2026-07-09 | 2026-07-15 | Completed | 2026-07-15 | bar: 2026-07-06 to 2026-07-13
W21 | PCC in Plinth | W20 | 2 | 2026-07-15 | 2026-07-17 | Completed | 2026-07-17 | bar: 2026-07-13
SUPERSTRUCTURE — GROUND FLOOR
W22 | Column Marking & Starter Work | W21 | 2 | 2026-07-17 | 2026-07-19 | Completed | 2026-07-19 | bar: 2026-07-13
W23 | Column Shuttering | W22 | 4 | 2026-07-19 | 2026-07-23 | Completed | 2026-07-23 | bar: 2026-07-13 to 2026-07-20
W24 | Column Steel Work | W23 | 5 | 2026-07-23 | 2026-07-28 | Completed | 2026-07-28 | bar: 2026-07-20 to 2026-07-27
W25 | Column Casting | W24 | 3 | 2026-07-28 | 2026-07-31 | Completed | 2026-07-31 | bar: 2026-07-27
W26 | Slab Shuttering | W25 | 15 | 2026-07-31 | 2026-08-15 | Completed | 2026-08-15 | bar: 2026-07-27 to 2026-08-10
W27 | Slab Steel | W26 | 10 | 2026-08-15 | 2026-08-25 | Completed | 2026-08-25 | bar: 2026-08-10 to 2026-08-24
W28 | Electrical Conduits Work | W27 | 2 | 2026-08-25 | 2026-08-27 | Completed | 2026-08-27 | bar: 2026-08-24
W29 | Checking of Steel | W28 | 1 | 2026-08-27 | 2026-08-28 | Completed | 2026-08-28 | bar: 2026-08-24
W30 | Casting of Slab incl. Staircase | W29 | 1 | 2026-08-28 | 2026-08-29 | Completed | 2026-08-29 | bar: 2026-08-24
SUPERSTRUCTURE — FIRST FLOOR
W31 | Column Marking & Starter Work | W30 | 2 | 2026-08-29 | 2026-08-31 | Completed | 2026-08-31 | bar: 2026-08-24 to 2026-08-31
W32 | Column Shuttering | W31 | 4 | 2026-08-31 | 2026-09-04 | Completed | 2026-09-04 | bar: 2026-08-31
W33 | Column Steel Work | W32 | 5 | 2026-09-04 | 2026-09-09 | Completed | 2026-09-09 | bar: 2026-08-31 to 2026-09-07
W34 | Column Casting | W33 | 3 | 2026-09-09 | 2026-09-12 | Completed | 2026-09-12 | bar: 2026-09-07
W35 | Slab Shuttering | W34 | 15 | 2026-09-12 | 2026-09-27 | In Progress | bar: 2026-09-07 to 2026-09-21
W36 | Slab Steel | W35 | 10 | 2026-09-27 | 2026-10-07 | Not Started | bar: 2026-09-21 to 2026-10-05
W37 | Electrical Conduits Work | W36 | 2 | 2026-10-07 | 2026-10-09 | Not Started | bar: 2026-10-05
W38 | Checking of Steel | W37 | 1 | 2026-10-09 | 2026-10-10 | Not Started | bar: 2026-10-05
W39 | Casting of Slab incl. Staircase | W38 | 1 | 2026-10-10 | 2026-10-11 | Not Started | bar: 2026-10-05
SUPERSTRUCTURE — SECOND FLOOR
W40 | Column Marking & Starter Work | W39 | 2 | 2026-10-11 | 2026-10-13 | Not Started | bar: 2026-10-05 to 2026-10-12
W41 | Column Shuttering | W40 | 4 | 2026-10-13 | 2026-10-17 | Not Started | bar: 2026-10-12
W42 | Column Steel Work | W41 | 3 | 2026-10-17 | 2026-10-20 | Not Started | bar: 2026-10-12 to 2026-10-19
W43 | Column Casting | W42 | 4 | 2026-10-20 | 2026-10-24 | Not Started | bar: 2026-10-19
W44 | Slab Shuttering | W43 | 15 | 2026-10-24 | 2026-11-08 | Not Started | bar: 2026-10-19 to 2026-11-02
W45 | Slab Steel | W44 | 10 | 2026-11-08 | 2026-11-18 | Not Started | bar: 2026-11-02 to 2026-11-16
W46 | Electrical Conduits Work | W45 | 2 | 2026-11-18 | 2026-11-20 | Not Started | bar: 2026-11-16
W47 | Checking of Steel | W46 | 1 | 2026-11-20 | 2026-11-21 | Not Started | bar: 2026-11-16
W48 | Casting of Slab incl. Staircase | W47 | 1 | 2026-11-21 | 2026-11-22 | Not Started | bar: 2026-11-16
SUPERSTRUCTURE — THIRD FLOOR
W49 | Column Marking & Starter Work | W48 | 2 | 2026-11-22 | 2026-11-24 | Not Started | bar: 2026-11-16 to 2026-11-23
W50 | Column Shuttering | W49 | 4 | 2026-11-24 | 2026-11-28 | Not Started | bar: 2026-11-23
W51 | Column Steel Work | W50 | 3 | 2026-11-28 | 2026-12-01 | Not Started | bar: 2026-11-23 to 2026-11-30
W52 | Column Casting | W51 | 4 | 2026-12-01 | 2026-12-05 | Not Started | bar: 2026-11-30
W53 | Slab Shuttering | W52 | 15 | 2026-12-05 | 2026-12-20 | Not Started | bar: 2026-11-30 to 2026-12-14
W54 | Slab Steel | W53 | 10 | 2026-12-20 | 2026-12-30 | Not Started | bar: 2026-12-14 to 2026-12-28
W55 | Electrical Conduits Work | W54 | 2 | 2026-12-30 | 2027-01-01 | Not Started | bar: 2026-12-28
W56 | Checking of Steel | W55 | 1 | 2027-01-01 | 2027-01-02 | Not Started | bar: 2026-12-28
W57 | Casting of Slab incl. Staircase | W56 | 1 | 2027-01-02 | 2027-01-03 | Not Started | bar: 2026-12-28
SUPERSTRUCTURE — FOURTH FLOOR
W58 | Column Marking & Starter Work | W57 | 2 | 2027-01-03 | 2027-01-05 | Not Started | bar: 2026-12-28 to 2027-01-04
W59 | Column Shuttering | W58 | 4 | 2027-01-05 | 2027-01-09 | Not Started | bar: 2027-01-04
W60 | Column Steel Work | W59 | 3 | 2027-01-09 | 2027-01-12 | Not Started | bar: 2027-01-04 to 2027-01-11
W61 | Column Casting | W60 | 4 | 2027-01-12 | 2027-01-16 | Not Started | bar: 2027-01-11
W62 | Slab Shuttering | W61 | 15 | 2027-01-16 | 2027-01-31 | Not Started | bar: 2027-01-11 to 2027-01-25
W63 | Slab Steel | W62 | 10 | 2027-01-31 | 2027-02-10 | Not Started | bar: 2027-01-25 to 2027-02-08
W64 | Electrical Conduits Work | W63 | 2 | 2027-02-10 | 2027-02-12 | Not Started | bar: 2027-02-08
W65 | Checking of Steel | W64 | 1 | 2027-02-12 | 2027-02-13 | Not Started | bar: 2027-02-08
W66 | Casting of Slab incl. Staircase | W65 | 1 | 2027-02-13 | 2027-02-14 | Not Started | bar: 2027-02-08
SUPERSTRUCTURE — TERRACE FLOOR
W67 | Column Marking & Starter Work | W66 | 2 | 2027-02-14 | 2027-02-16 | Not Started | bar: 2027-02-08 to 2027-02-15
W68 | Column Shuttering | W67 | 4 | 2027-02-16 | 2027-02-20 | Not Started | bar: 2027-02-15
W69 | Column Steel Work | W68 | 3 | 2027-02-20 | 2027-02-23 | Not Started | bar: 2027-02-15 to 2027-02-22
W70 | Column Casting | W69 | 4 | 2027-02-23 | 2027-02-27 | Not Started | bar: 2027-02-22
W71 | Slab Shuttering | W70 | 15 | 2027-02-27 | 2027-03-14 | Not Started | bar: 2027-02-22 to 2027-03-08
W72 | Slab Steel | W71 | 10 | 2027-03-14 | 2027-03-24 | Not Started | bar: 2027-03-08 to 2027-03-22
W73 | Electrical Conduits Work | W72 | 2 | 2027-03-24 | 2027-03-26 | Not Started | bar: 2027-03-22
W74 | Checking of Steel | W73 | 1 | 2027-03-26 | 2027-03-27 | Not Started | bar: 2027-03-22
W75 | Casting of Slab incl. Staircase | W74 | 1 | 2027-03-27 | 2027-03-28 | Not Started | bar: 2027-03-22
SUPERSTRUCTURE — MUMTY FLOOR
W76 | Column Marking & Starter Work | W75 | 2 | 2027-03-28 | 2027-03-30 | Not Started | bar: 2027-03-22 to 2027-03-29
W77 | Column Shuttering | W76 | 4 | 2027-03-30 | 2027-04-03 | Not Started | bar: 2027-03-29
W78 | Column Steel Work | W77 | 3 | 2027-04-03 | 2027-04-06 | Not Started | bar: 2027-03-29 to 2027-04-05
W79 | Column Casting | W78 | 4 | 2027-04-06 | 2027-04-10 | Not Started | bar: 2027-04-05
W80 | Slab Shuttering | W79 | 7 | 2027-04-10 | 2027-04-17 | Not Started | bar: 2027-04-05 to 2027-04-12
W81 | Slab Steel | W80 | 7 | 2027-04-17 | 2027-04-24 | Not Started | bar: 2027-04-12 to 2027-04-19
W82 | Electrical Conduits Work | W81 | 2 | 2027-04-24 | 2027-04-26 | Not Started | bar: 2027-04-19 to 2027-04-26
W83 | Checking of Steel | W82 | 1 | 2027-04-26 | 2027-04-27 | Not Started | bar: 2027-04-26
W84 | Casting of Slab incl. Staircase | W83 | 1 | 2027-04-27 | 2027-04-28 | Not Started | bar: 2027-04-26
Baseline logic: each activity is finish-to-start linked to its predecessor. Start = predecessor Finish; Finish = Start + Duration. Edit any Duration (col D) or the Baseline Start (B7) and the whole chain re-sequences.
Calendar-day model (no non-working days), reproducing the contractor programme as issued. Curing / striking float and monsoon contingency not embedded — flagged separately. Completion dates are taken as programmed; site visits V04F01-02→06 corroborate the frame tracking the baseline (footings→1st-floor columns cast, 1st-floor slab in progress).
STATUS @ ENTRY / DATE OF COMPLETION reflect progress as of 18-Sep-2026 (site visit V04F01-06). Grey bar = activity fully completed; black bar = not yet complete (in progress or not started). Thick vertical line marks the as-of date.
volecule.com ¦ info@volecule.com ¦ +91-8383893877