## Scheduler Zero
VOLECULE
We don't execute. We only verify.
PROJECT | V04F01 — Madhav Arambol Residence (S+4 + Terrace + Mumty), Arambol, Goa |  |  |  | FRAME FINISH
DOCUMENT | Scheduler Zero (Sch-0) — Baseline Structural Programme ¦ Doc: V04F01-03 |  |  |  | 2027-04-28
BASIS | Contractor structural programme (footings → mumty). Frame only — excludes finishes, waterproofing, MEP fit-out & handover. |  |  |  | 366
BASELINE START | 2026-04-27
[6 empty] | APR 2026 | MAY 2026 |  |  |  | JUN 2026 |  |  |  |  | JUL 2026 |  |  |  | AUG 2026 |  |  |  |  | SEP 2026 |  |  |  | OCT 2026 |  |  |  | NOV 2026 |  |  |  |  | DEC 2026 |  |  |  | JAN 2027 |  |  |  | FEB 2027 |  |  |  | MAR 2027 |  |  |  |  | APR 2027
WORK | ACTIVITY | PRED. | DUR (d) | START | FINISH | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26
FOUNDATION & SUBSTRUCTURE
W1 | Excavation in Hard Rock up to 1.5 m (Footings) | — | 7 | 2026-04-27 | 2026-05-04
W2 | Soiling | W1 | 4 | 2026-05-04 | 2026-05-08
W3 | PCC for Footings | W2 | 4 | 2026-05-08 | 2026-05-12
W4 | Shuttering for Footing Boxes | W3 | 7 | 2026-05-12 | 2026-05-19
W5 | Tieing of Foundation Jaali & Column | W4 | 7 | 2026-05-19 | 2026-05-26
W6 | Checking of Steel | W5 | 1 | 2026-05-26 | 2026-05-27
W7 | Casting of Footings | W6 | 1 | 2026-05-27 | 2026-05-28
R.C.C. WORKS — STUB COLUMN & PLINTH
W8 | Line-out & Starter for Stub Column | W7 | 2 | 2026-05-28 | 2026-05-30
W9 | Shuttering for Stub Column | W8 | 4 | 2026-05-30 | 2026-06-03
W10 | Casting of Stub Column | W9 | 2 | 2026-06-03 | 2026-06-05
W11 | Excavation of Plinth Beams | W10 | 4 | 2026-06-05 | 2026-06-09
W12 | PCC Below | W11 | 4 | 2026-06-09 | 2026-06-13
W13 | Masonry Below Plinth | W12 | 6 | 2026-06-13 | 2026-06-19
W14 | Shuttering for Plinth Beam | W13 | 7 | 2026-06-19 | 2026-06-26
W15 | Tieing of Reinforcement | W14 | 5 | 2026-06-26 | 2026-07-01
W16 | Checking of Steel | W15 | 1 | 2026-07-01 | 2026-07-02
W17 | Concreting of Plinth Beam | W16 | 2 | 2026-07-02 | 2026-07-04
W18 | De-shuttering of Plinth Beam | W17 | 1 | 2026-07-04 | 2026-07-05
W19 | Backfilling in Plinth | W18 | 4 | 2026-07-05 | 2026-07-09
W20 | Rubble Soling in Plinth | W19 | 6 | 2026-07-09 | 2026-07-15
W21 | PCC in Plinth | W20 | 2 | 2026-07-15 | 2026-07-17
SUPERSTRUCTURE — GROUND FLOOR
W22 | Column Marking & Starter Work | W21 | 2 | 2026-07-17 | 2026-07-19
W23 | Column Shuttering | W22 | 4 | 2026-07-19 | 2026-07-23
W24 | Column Steel Work | W23 | 5 | 2026-07-23 | 2026-07-28
W25 | Column Casting | W24 | 3 | 2026-07-28 | 2026-07-31
W26 | Slab Shuttering | W25 | 15 | 2026-07-31 | 2026-08-15
W27 | Slab Steel | W26 | 10 | 2026-08-15 | 2026-08-25
W28 | Electrical Conduits Work | W27 | 2 | 2026-08-25 | 2026-08-27
W29 | Checking of Steel | W28 | 1 | 2026-08-27 | 2026-08-28
W30 | Casting of Slab incl. Staircase | W29 | 1 | 2026-08-28 | 2026-08-29
SUPERSTRUCTURE — FIRST FLOOR
W31 | Column Marking & Starter Work | W30 | 2 | 2026-08-29 | 2026-08-31
W32 | Column Shuttering | W31 | 4 | 2026-08-31 | 2026-09-04
W33 | Column Steel Work | W32 | 5 | 2026-09-04 | 2026-09-09
W34 | Column Casting | W33 | 3 | 2026-09-09 | 2026-09-12
W35 | Slab Shuttering | W34 | 15 | 2026-09-12 | 2026-09-27
W36 | Slab Steel | W35 | 10 | 2026-09-27 | 2026-10-07
W37 | Electrical Conduits Work | W36 | 2 | 2026-10-07 | 2026-10-09
W38 | Checking of Steel | W37 | 1 | 2026-10-09 | 2026-10-10
W39 | Casting of Slab incl. Staircase | W38 | 1 | 2026-10-10 | 2026-10-11
SUPERSTRUCTURE — SECOND FLOOR
W40 | Column Marking & Starter Work | W39 | 2 | 2026-10-11 | 2026-10-13
W41 | Column Shuttering | W40 | 4 | 2026-10-13 | 2026-10-17
W42 | Column Steel Work | W41 | 3 | 2026-10-17 | 2026-10-20
W43 | Column Casting | W42 | 4 | 2026-10-20 | 2026-10-24
W44 | Slab Shuttering | W43 | 15 | 2026-10-24 | 2026-11-08
W45 | Slab Steel | W44 | 10 | 2026-11-08 | 2026-11-18
W46 | Electrical Conduits Work | W45 | 2 | 2026-11-18 | 2026-11-20
W47 | Checking of Steel | W46 | 1 | 2026-11-20 | 2026-11-21
W48 | Casting of Slab incl. Staircase | W47 | 1 | 2026-11-21 | 2026-11-22
SUPERSTRUCTURE — THIRD FLOOR
W49 | Column Marking & Starter Work | W48 | 2 | 2026-11-22 | 2026-11-24
W50 | Column Shuttering | W49 | 4 | 2026-11-24 | 2026-11-28
W51 | Column Steel Work | W50 | 3 | 2026-11-28 | 2026-12-01
W52 | Column Casting | W51 | 4 | 2026-12-01 | 2026-12-05
W53 | Slab Shuttering | W52 | 15 | 2026-12-05 | 2026-12-20
W54 | Slab Steel | W53 | 10 | 2026-12-20 | 2026-12-30
W55 | Electrical Conduits Work | W54 | 2 | 2026-12-30 | 2027-01-01
W56 | Checking of Steel | W55 | 1 | 2027-01-01 | 2027-01-02
W57 | Casting of Slab incl. Staircase | W56 | 1 | 2027-01-02 | 2027-01-03
SUPERSTRUCTURE — FOURTH FLOOR
W58 | Column Marking & Starter Work | W57 | 2 | 2027-01-03 | 2027-01-05
W59 | Column Shuttering | W58 | 4 | 2027-01-05 | 2027-01-09
W60 | Column Steel Work | W59 | 3 | 2027-01-09 | 2027-01-12
W61 | Column Casting | W60 | 4 | 2027-01-12 | 2027-01-16
W62 | Slab Shuttering | W61 | 15 | 2027-01-16 | 2027-01-31
W63 | Slab Steel | W62 | 10 | 2027-01-31 | 2027-02-10
W64 | Electrical Conduits Work | W63 | 2 | 2027-02-10 | 2027-02-12
W65 | Checking of Steel | W64 | 1 | 2027-02-12 | 2027-02-13
W66 | Casting of Slab incl. Staircase | W65 | 1 | 2027-02-13 | 2027-02-14
SUPERSTRUCTURE — TERRACE FLOOR
W67 | Column Marking & Starter Work | W66 | 2 | 2027-02-14 | 2027-02-16
W68 | Column Shuttering | W67 | 4 | 2027-02-16 | 2027-02-20
W69 | Column Steel Work | W68 | 3 | 2027-02-20 | 2027-02-23
W70 | Column Casting | W69 | 4 | 2027-02-23 | 2027-02-27
W71 | Slab Shuttering | W70 | 15 | 2027-02-27 | 2027-03-14
W72 | Slab Steel | W71 | 10 | 2027-03-14 | 2027-03-24
W73 | Electrical Conduits Work | W72 | 2 | 2027-03-24 | 2027-03-26
W74 | Checking of Steel | W73 | 1 | 2027-03-26 | 2027-03-27
W75 | Casting of Slab incl. Staircase | W74 | 1 | 2027-03-27 | 2027-03-28
SUPERSTRUCTURE — MUMTY FLOOR
W76 | Column Marking & Starter Work | W75 | 2 | 2027-03-28 | 2027-03-30
W77 | Column Shuttering | W76 | 4 | 2027-03-30 | 2027-04-03
W78 | Column Steel Work | W77 | 3 | 2027-04-03 | 2027-04-06
W79 | Column Casting | W78 | 4 | 2027-04-06 | 2027-04-10
W80 | Slab Shuttering | W79 | 7 | 2027-04-10 | 2027-04-17
W81 | Slab Steel | W80 | 7 | 2027-04-17 | 2027-04-24
W82 | Electrical Conduits Work | W81 | 2 | 2027-04-24 | 2027-04-26
W83 | Checking of Steel | W82 | 1 | 2027-04-26 | 2027-04-27
W84 | Casting of Slab incl. Staircase | W83 | 1 | 2027-04-27 | 2027-04-28
Baseline logic: each activity is finish-to-start linked to its predecessor. Start = predecessor Finish; Finish = Start + Duration. Edit any Duration (col D) or the Baseline Start (B7) and the whole chain re-sequences.
Calendar-day model (no non-working days), reproducing the contractor programme as issued. Curing / striking float and monsoon contingency not embedded — flagged separately.
volecule.com ¦ info@volecule.com ¦ +91-8383893877